## Catalog
Index | Type | Name | Description | HISTORY Update Document
1 | Design UI/UX | Landing Page |  | 0.2 | 2022-08-23 | HaoVT
2 |  | Login Page |  | 0.3
3 |  | Create Account Page
4 |  | Dashboard Page
5 |  | "Cari Jurusan" Page
6 |  | College Details Page
7 |  | Test 1 Page
8 |  | Test 2 Page
9 |  | "Colleges of The Year" Page
10 | Data | Data Colleges
11 |  | Question Test 1
12 |  | Question Test 2
13 | Development | Landing Page
14 |  | Login Page
15 |  | Create Account Page
16 |  | Dashboard Page
17 |  | "Cari Jurusan" Page
18 |  | College Details Page
19 |  | Test 1 Page
20 |  | Test 2 Page
21 |  | "Colleges of The Year" Page
22 | Testing | System Integration Test
23 |  | User Acceptance Test

## Project Schedule
[MauKuliah - Sprint 1 ] Project Schedule
WBS | Task | Start | End | Cal Days | % Done
1 | Design UI/UX | 2022-09-01 | 2022-09-09 | 9
1.1 | Landing Page | 2022-09-01 | 2022-09-01 | 1 | %
1.2 | Login Page | 2022-09-01 | 2022-09-01 | 1 | %
1.3 | Create Account Page | 2022-09-01 | 2022-09-01 | 1 | %
1.4 | Dashboard Page | 2022-09-02 | 2022-09-02 | 1 | %
1.5 | "Cari Jurusan" Page | 2022-09-02 | 2022-09-02 | 1 | %
1.6 | College Details Page | 2022-09-05 | 2022-09-06 | 2 | %
1.7 | Test 1 Page | 2022-09-06 | 2022-09-08 | 3 | %
1.8 | Test 2 Page | 2022-09-08 | 2022-09-09 | 2 | %
1.9 | "Colleges of The Year" Page | 2022-09-02 | 2022-09-02 | 1 | %
2 | Data | 2022-09-01 | 2022-09-09 | 9
2.1 | Data Colleges | 2022-09-01 | 2022-09-05 | 5 | %
2.2 | Data Colleges of The Year | 2022-09-01 | 2022-09-02 | 2
2.3 | Data Highlight Alumni from Colleges | 2022-09-01 | 2022-09-02 | 2 | %
2.4 | Question Test 1 | 2022-09-05 | 2022-09-07 | 3 | %
2.5 | Question Test 2 | 2022-09-07 | 2022-09-09 | 3 | %
3 | Development | 2022-09-01 | 2022-09-16 | 16
3.1 | Create Database | 2022-09-01 | 2022-09-02 | 2 | %
3.2 | Landing Page | 2022-09-05 | 2022-09-06 | 2 | %
3.3 | Login Page | 2022-09-05 | 2022-09-06 | 2 | %
3.4 | Create Account Page | 2022-09-05 | 2022-09-06 | 2 | %
3.5 | Dashboard Page | 2022-09-06 | 2022-09-07 | 2 | %
3.6 | "Cari Jurusan" Page | 2022-09-07 | 2022-09-07 | 1 | %
3.7 | College Details Page | 2022-09-08 | 2022-09-09 | 2 | %
3.8 | Test 1 Page | 2022-09-12 | 2022-09-14 | 3 | %
3.9 | Test 2 Page | 2022-09-14 | 2022-09-16 | 3 | %
3.10 | "Colleges of The Year" Page | 2022-09-06 | 2022-09-07 | 2 | %
4 | System Integrated Test | 2022-09-05 | 2022-09-23 | 19
4.1 | Create Test Cases | 2022-09-05 | 2022-09-09 | 5 | %
4.2 | Test Mobile iOS - Android | 2022-09-19 | 2022-09-20 | 2 | %
4.3 | Test Web Safari - Chrome - Firefox | 2022-09-21 | 2022-09-23 | 3 | %
4.4 | Fixing Bug Mobile | 2022-09-19 | 2022-09-21 | 3 | %
4.5 | Fixing Bug Web | 2022-09-21 | 2022-09-23 | 3 | %
4.6 | Retest after fixing Mobile | 2022-09-22 | 2022-09-23 | 2 | %
4.7 | Retest after fixing Web | 2022-09-23 | 2022-09-24 | 2 | %
5 | User Acceptance Test | 2022-09-12 | 2022-09-30 | 19
5.1 | Create Test Cases | 2022-09-12 | 2022-09-16 | 5 | %
5.2 | Test Mobile iOS - Android | 2022-09-26 | 2022-09-27 | 2 | %
5.3 | Test Web Safari - Chrome - Firefox | 2022-09-28 | 2022-09-29 | 2 | %
5.4 | Fixing Bug Mobile | 2022-09-26 | 2022-09-28 | 3 | %
5.5 | Fixing Bug Web | 2022-09-28 | 2022-09-30 | 3 | %
5.6 | Retest after fixing Mobile | 2022-09-28 | 2022-09-29 | 2 | %
5.7 | Retest after fixing Web | 2022-09-29 | 2022-09-30 | 2 | %
Formulas:
Start = MIN([Start, row below]:C13)
End = MAX([End, row below]:D13)
End = [Start]+[Cal Days]-1
Note on A3: Work Breakdown Structure: Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, Level 3: 1.1.1, 1.1.2, The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B3: Task: Enter the name of each task and sub-task. Use spaces to indent sub-tasks.
Note on C3: Task Start Date: You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on D3: End Date: Calculated based on the Start Date and the duration of the task.
Note on E3: Duration: The duration is the number of calendar days for the given task.
Note on F3: Percent Complete: Update the status of this task by entering the percent complete (between 0% and 100%).